# Sprint 1 — Prototype Prep Claude Code Macro Pad · Fan Project Dates: 8 Apr 2026 — 17 Apr 2026 (10 days) · Solo maker · Magnus

Sprint Goal Have the JLCPCB prototype order ready to place — CAD finalised, PCB designed in EasyEDA, colour confirmed via swatch, and all external components sourced.

## Capacity

Solo project — hours estimated as focused side-project sessions. Planning to 75% capacity to absorb iteration on CAD tolerances and PCB routing.

| Who | Available Hours | Planned Load | Notes |
| --- | --- | --- | --- |
| Magnus | ~15 hrs | 11 hrs (75%) | Side project — ~1.5 hrs/day focused sessions |
| TOTAL | 15 hrs | 11 hrs | 25% buffer for iteration + unexpected blockers |

## Sprint Backlog

Ordered by dependency chain — items must complete in sequence where noted. P0 = sprint fails without it. P1 = sprint goal at risk. P2 = stretch.

| Pri | Task | Est. | Seq. | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| P0 | DM original X creator — align on collaboration before any build work | 30 min | Day 1 — blocks all | Explicit greenlight received. Arrangement agreed (min: free unit + credit). No ambiguity on IP/promotion. |
| P0 | Order FDM ASA colour test swatch from JLCPCB — orange + red-orange, 50 × 50 mm flat prints | 15 min | Day 1–2 — parallel | Two swatches ordered. Can proceed with CAD while swatches ship — compare against #DA7756 (218/119/86) on arrival. |
| P0 | Finalise case CAD — robot silhouette, two-part case (tray + top plate), all cut-outs and tolerances | 5–6 hrs | Day 2–6 — needs Day 1 | Top plate: 5× MX cut-outs (14.5 × 14.5 mm), 2× encoder holes (7 mm ø), USB-C slot. Tray: M2 boss inserts, PCB standoffs at 3 mm, 2.5 mm walls (3 mm at arm joints). Silhouette matches render dimensions (120 × 66 × 8.6 mm tray). |
| P0 | PCB design in EasyEDA — schematic + layout for Pro Micro macro pad with 5 switches and 2 encoders | 3–4 hrs | Day 5–8 — after CAD | Schematic: Pro Micro footprint, 5× 1N4148 diodes, 5× Kailh hotswap, 2× EC11, RESET button. Layout: custom non-rectangular silhouette (114.5 × 49 mm), DRC clean, Gerbers exportable. EasyEDA project saved. |
| P1 | Source external components — Pro Micro, EC11 encoders, black metal knobs, black PBT keycaps | 1 hr | Day 3–5 — parallel | Cart confirmed on LCSC (Pro Micro USB-C, EC11 × 2), AliExpress (knobs × 2, 16 mm ø black anodised aluminium), KBDFans or equivalent (4× 1U + 1× 1.75U black PBT blank). Not yet ordered — confirm after CAD finalised. |
| P1 | QMK firmware skeleton — basic config, keymap, encoder map | 1–2 hrs | Day 6–9 — after PCB | QMK repo forked/cloned. config.h with correct matrix size and encoder count. Basic keymap compiles without errors. Encoder map: left = volume, right = placeholder. Does not need to be flashed this sprint. |
| P2 | STRETCH: Place the JLCPCB prototype order — PCB + PCBA + FDM ASA case | 30 min | Day 9–10 — needs all P0 | Stretch goal only if colour swatch arrives and is approved before end of sprint. Order includes PCB (1.6 mm FR4 ENIG), PCBA (hotswap sockets + diodes populated), FDM ASA case in confirmed colour. |

Planned load: 11 hrs  ·  Capacity: 15 hrs  ·  Sprint load: 73% of capacity

## Critical Path

| Step | Day | What Unlocks |
| --- | --- | --- |
| DM creator | 1 | Everything — if they say no or go quiet, sprint scope changes entirely |
| Colour swatch order | 1 | Can be ordered same day, ships while CAD is in progress |
| CAD complete | 6 | PCB layout needs accurate mounting hole positions from CAD |
| PCB layout complete | 8 | Gerbers ready to upload; firmware can be written against finalised matrix |
| Swatch arrives + approved | ~8 | Confirms FDM ASA colour for JLCPCB case order — unlocks stretch P2 |
| JLCPCB order placed (stretch) | 10 | Prototype in production — sprint complete |

## Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Creator declines or goes quiet | Low | Sprint goal pivots — lose launch amplification | Have a backup plan: launch independently with a clear 'inspired by' framing. Start DM Day 1. |
| CAD tolerances wrong for FDM ASA | Medium | Case and PCB don't fit — delays prototype order | Add 0.2 mm clearance on all mating faces. Design case in two halves to allow reprinting one part only. |
| Colour swatch doesn't arrive before sprint ends | Medium | JLCPCB order can't be placed this sprint | This only affects the stretch P2 goal — core sprint deliverables (CAD + PCB) are unaffected. Order swatch Day 1. |
| EC11 encoder footprint mismatch in EasyEDA | Low | PCB layout error, requires respin | Verify encoder pin pitch against LCSC part datasheet before placing footprint. Cross-check against EC11 mechanical drawing. |

## Definition of Done

- Creator greenlight confirmed in writing (DM screenshot or similar)

- Case CAD exported as STEP + STL — ready to upload to JLCPCB

- PCB EasyEDA project DRC-clean — Gerbers generated and verified

- Colour swatch compared against #DA7756 — winning filament noted in spec doc

- Component carts confirmed (LCSC + AliExpress + keycap supplier) — not yet ordered

- QMK config compiles — basic keymap and encoder map in place

- JLCPCB order placed (stretch only — not required for sprint success)

## Key Dates

| Date | Event |
| --- | --- |
| 8 Apr 2026 | Sprint start — DM creator + order colour swatch immediately |
| 13 Apr 2026 | Mid-sprint check-in — CAD should be at 80%+, PCB routing started |
| ~15 Apr 2026 | Colour swatch expected to arrive from JLCPCB |
| 17 Apr 2026 | Sprint end — all P0 + P1 items complete; P2 if swatch arrived |

Fan project — not affiliated with or endorsed by Anthropic. Claude and Claude Code are trademarks of Anthropic, PBC.